## TestSchedule (hidden)
# | Milestone Task | PIC | Effort (pd) |  |  | Status | Deliverables Date | Notes
|  |  |  | Start Date | End Date
1 | Create Test Plan | DuongTTT | 1 | 2021-05-10 | 2021-05-10 | Done
2 | Review Test plan | HoangLS | 0.25 | 2021-05-14 | 2021-05-14 | Done
3 | Update Test plan | DuongTTT | 0.25 | 2021-05-17 | 2021-05-17 | Done
4 | Create Integration Test case | KhuyenTL LyDT NgaNT2 | 10.1667 | 2021-05-21 | 2021-06-07 | InProgress
5 | Review Integration Test case | DuongTTT | 1.0167 | 2021-05-25 | 2021-06-07
6 | Update Integration Test case | KhuyenTL LyDT NgaNT2 | 1.0167 | 2021-05-26 | 2021-06-07
7 | Execute Integration Test | KhuyenTL LyDT NgaNT2 | #REF! | 2021-06-01 | 2021-06-14
8 | Verify Integration Bugs | KhuyenTL LyDT NgaNT2 | #REF! | 2021-06-02 | 2021-06-21
9 | Execute System Test | KhuyenTL LyDT NgaNT2 | 0 | 2021-06-15 | 2021-06-18
10 | Execute Regression Test | KhuyenTL LyDT NgaNT2 | 0 | 2021-06-18 | 2021-06-21 |  |  | Based on solution of Dev Team
11 | Create UAT Scenario | KhuyenTL | 2.0333 | 2021-06-15 | 2021-06-17
12 | Review UAT Scenario | DuongTTT | 0.20333 | 2021-06-16 | 2021-06-17
13 | Update UAT Scenario | KhuyenTL | 0.20333 | 2021-06-17 | 2021-06-18
14 | Verify UAT Bugs | KhuyenTL LyDT NgaNT2 | #REF! | 2021-06-22 | 2021-06-25
#REF!

## QC_SprintRoadmap (hidden)
Sprint | Start Date | End Date | Dev 's Goal | Status | QC' Goal | Status | QC's output | Notes
Sprint 1 | 2021-04-19 | 2021-04-25
Sprint 2 | 2021-04-26 | 2021-04-29
Sprint 3 | 2021-05-04 | 2021-05-07
Sprint 4 | 2021-05-10 | 2021-05-14 | Setup Empty Store |  | Understand requirement
Sprint 5 | 2021-05-18 | 2021-05-24 | Completed Setup Empty Store: Setup theme site for Chile OBS Customer Register/Login Product & Catalog Setup (LG to provide product attributes) Product Pricing : tax, promotion Shipping Method & Shipping Fee | Yellow | + Create Test Plan + Create Empty Store CheckList | Yellow | Features's Checklist | Dev: - Customer Register/Login : Block - Test: - Empty Store CheckList hasn't completed (need review)
Sprint 6 | 2021-05-25 | 2021-05-31 | FE buy page Buy Page Integration Inventory Management (ERP Integration): Single/Multiple Warehouse SSO Integration Payment Gateway Integration: Vector Invoice Processing Transportation Management: 3PL intergration Shipping Method & Shipping Fee Customer Register/Login GERP>OBS : Product Management | Green | + Execute Empty Store CheckList + 1st Demo (of Sprint): 24->28/5: empty Store + Create TCs of Product creating + Create TCs of Sale operation + Create TC of My Account | Green | OMV_Product OMD_Product PTO_Product Configurable_Product LG.COM Interface GERP Interface Shopping Cart Checkout_Delivery Info Checkout_Payment Checkout_Order Confirmation My Account_My Coupons My Account_View Details My Account_VIP Program My Account_My Orders My Account_My Returns My Account_My Refund My Account_Others My Account_Inquiries | 24 ~ 26/6: STG2 GP2 doesn't work
Sprint 7 | 2021-06-01 | 2021-06-07 | Content Preparation Data Migration (Customer, Product) Prepare product content on LG.com Prepare product content on Magento Prepare CMS content on LG.com 1 Localization (Frontend only) Payment Gateway Integration: Vector Invoice Processing --------------------------------------- - https://jira.smartosc.com/browse/LGOBSSI-142 [Chile OBS] Customer Register/Login - https://jira.smartosc.com/browse/LGOBSSI-621 [Chile OBS] Shopping Cart - https://jira.smartosc.com/browse/LGOBSSI-622 [Chile OBS] Admin is able to manage Delivery - https://jira.smartosc.com/browse/LGOBSSI-623 [Chile OBS] Checkout - Delivery Info - https://jira.smartosc.com/browse/LGOBSSI-144 [Chile OBS] Product Pricing: tax - https://jira.smartosc.com/browse/LGOBSSI-325 [Chile OBS] Product Pricing : promotion - https://jira.smartosc.com/browse/LGOBSSI-143 [Chile OBS] Product Management | Green | + 1st Testing(TC&Execute): deadline 3/6 - Execute TCs of Product creating - Execute TCs of Sale operation + 2nd Testing(TC): 4/6 => Payment Gateway Integration: Vector; Invoice Processing; 1 Localization (Frontend only) + 2nd Demo: 4/6 + 2nd Testing(TC): 4/6 - Create TC of Admin & Store - Create TC of FE (HTML, UI) ------------------- Create TCs and Execute test: - https://jira.smartosc.com/browse/LGOBSSI-142 [Chile OBS] Customer Register/Login - https://jira.smartosc.com/browse/LGOBSSI-621 [Chile OBS] Shopping Cart - https://jira.smartosc.com/browse/LGOBSSI-622 [Chile OBS] Admin is able to manage Delivery - https://jira.smartosc.com/browse/LGOBSSI-623 [Chile OBS] Checkout - Delivery Info - https://jira.smartosc.com/browse/LGOBSSI-144 [Chile OBS] Product Pricing: tax - https://jira.smartosc.com/browse/LGOBSSI-325 [Chile OBS] Product Pricing : promotion - https://jira.smartosc.com/browse/LGOBSSI-143 [Chile OBS] Product Management | Green | Admin_Dashboard Admin_SALES_Orders Admin_SALES_Invoices Admin_SALES_Shipments Admin_SALES_Returns Admin_SALES_Credit Memos Admin_Product Admin_PostCode Admin_Customer Admin_MARKETING STORES_General Others_FEPages UI -------------------- Testcase for 7 tickets Test result for 7 tickets
Sprint 8 | 2021-06-08 | 2021-06-14 | Fix Functional's Bug | Green | + 2nd Testing (Execute): 17/6 - Execute TC of Admin & Store - Execute TC of FE (HTML, UI) + Verify functional bug fixed | Green
Sprint 9 | 2021-06-15 | 2021-06-21 | Performance Test Review distribution of users to scenarios Setup test scenarios Perform load test, fix bugs and report Security test Fix bugs from test result feedback | Green | '+ 3rd Demo: overall + System Test: 14-18/6 + Regression Test: 14-18/6 + Prepare UAT file | Green
Sprint 10 | 2021-06-22 | 2021-06-30 | Fix UAT's bug | Green | UAT | Green

## TestEstimation (hidden)
# | Feature | TestCase |  |  |  | Execute | [7 empty] | Status | Deliverables Date
|  | Plan | Created | To Do | Effort (pd) | Plan | Pass | Fail | Untested | N/A | Effort (pd) | Start Date | End Date
1 | Empty Store CheckList | 20 | #REF! | #REF! | 0.33333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | OMD_Product | 20 | 35 | -15 | 0.33333 | 35 | 0 | 0 | 35 | 160 | 1.1667
3 | OMV_Product | 20 | 40 | -20 | 0.33333 | 40 | 1 | 0 | 39 | 156 | 1.3333
4 | PTO_ Product | 20 | 40 | -20 | 0.33333 | 40 | 1 | 0 | 39 | 156 | 1.3333
5 | Configurable_Product | 10 | 40 | -30 | 0.16667 | 40 | 1 | 0 | 39 | 156 | 1.3333
6 | Shopping Cart | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
7 | Checkout_Delivery Info | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
8 | Checkout_Payment | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
9 | Checkout_Order Confirmation | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
10 | My Account_My Coupons | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
11 | My Account_View Details | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
12 | My Account_VIP Program | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
13 | My Account_My Orders | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
14 | My Account_My Returns | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
15 | My Account_My Refund | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
16 | My Account_Others | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
17 | My Account_Inquiries | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
18 | Others_FEPages | 15 |  |  | 0.25 | 15 |  |  |  |  | 0.5
19 | Admin_Dashboard | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
20 | Admin_SALES_Orders | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
21 | Admin_SALES_Invoices | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
22 | Admin_SALES_Shipments | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
23 | Admin_SALES_Returns | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
24 | Admin_SALES_Credit Memos | 5 |  |  | 0.083333 | 5 |  |  |  |  | 0.16667
25 | Admin_Product | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
26 | Admin_PostCode | 10 |  |  | 0.16667 | 10 |  |  |  |  | 0.33333
27 | Admin_Customer | 20 |  |  | 0.33333 | 20 |  |  |  |  | 0.66667
28 | Admin_MARKETING | 50 |  |  | 0.83333 | 50 |  |  |  |  | 1.6667
29 | STORES_General | 50 |  |  | 0.83333 | 50 |  |  |  |  | 1.6667
30 | LG.COM Interface | 50 |  |  | 0.83333 | 50 |  |  |  |  | 1.6667
31 | GERP Interface | 50 |  |  | 0.83333 | 50 |  |  |  |  | 1.6667
|  | 610 | #REF! | #REF! | 10.1667 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Normal Test average:
| Create TCs | 60
| Execute TCs | 30

## TestMatrix (hidden)
Area | Category1 | Category2 | No | Function | Description | Required(Y/N) | Test Sheet | Test Case
Customer Front Page | Shopping Cart |  | 1 | Save for later | Logged in customer can move an item in their cart to their “Save for later” list for later purchase | Yes | Shopping Cart
|  |  | 2 | Remove Item | Customer can remove a product from their cart | Yes | Shopping Cart
|  |  | 3 | Change the quantity | Customer can change quantity of the items in their cart | Yes | Shopping Cart
|  |  | 4 | Delivery Check | Customer can enter their delivery location on cart page to check whether their location can be delivered to and stock is available for that area Delivery location could be: postcode, pincode, delivery area | No | Shopping Cart
|  |  | 5 | Cart Promo - Automated Rule | Customer can view applied automated promotion on cart page | No | Shopping Cart
|  |  | 6 | Cart Promo - Single Coupon | Customer can apply single coupon on cart page | Yes | Shopping Cart
|  |  | 7 | Cart Promo - Multiple Coupons | Customer can apply multiple coupons on cart page | No | Shopping Cart
|  |  | 8 | Cross-sell | Customer can view cross-sell products on Cart Page | Yes | Shopping Cart
| Checkout | Delivery Info | 9 | Guest Checkout | Customer can checkout as guest | Yes | Checkout_Delivery Info
|  |  | 10 | Auto-completed shipping address | Customer can have their shipping address automatically completed for faster checkout | No | Checkout_Delivery Info
|  |  | 11 | Shipping Method | Customer can select their preferred shipping method provided by the country | No | Checkout_Delivery Info
|  |  | 12 | Installation | Customer can request installation service for their purchasing product if applicable | Yes | Checkout_Delivery Info
|  |  | 13 | Haulaway | Customer can request Haulaway service for their purchasing product if applicable | No | Checkout_Delivery Info
|  |  | 14 | Delivery Fee | Customer can view their delivery fee calculated by system after providing all delivery information | Yes | Checkout_Delivery Info
|  | Payment | 15 | Credit Card - One Time | Customer can pay one time with their credit/debit card | Yes | Checkout_Payment
|  |  | 16 | Credit Card - Installments | Customer can pay in multiple installments with their credit/debit card when applicable | Yes | Checkout_Payment
|  |  | 17 | Bank Transfer | Customer can pay by bank transfer | No | Checkout_Payment
|  |  | 18 | Other Payment method | Customer can pay by other payment method(s) | Credit or Debit Card | Checkout_Payment
|  |  | 19 | Agreement | Customer can view and must agree to T&Cs and Privacy Policies in order to place order on OBS website | Yes | Checkout_Payment
|  |  | 20 | Newsletter Subscription | Customer can choose to subscribe to OBS’ newsletter on Payment page if they want | Yes | Checkout_Payment
|  | Order Confirmation | 21 | Order Complete | Customer will be explicitly informed on the site about their order completion once Payment has been processed successfully Customer will receive an email once the check-out is complete | Yes | Checkout_Order Confirmation
|  |  | 22 | Cross-sell | Customer sees cross selling products and is able to add them to cart | Yes | Checkout_Order Confirmation
| My Account | My Coupons | 23 | View My Coupon | Customer can view their list of coupons | No | My Account_My Coupons
|  | View Details | 24 | View Addresses | Customer can view up to 5 of their last saved addresses | Yes | My Account_View Details
|  |  | 25 | Add New Address | Customer can add a new address to their address book | Yes | My Account_View Details
|  |  | 26 | Delete an Address | Customer can delete an existing address in their address book | Yes | My Account_View Details
|  |  | 27 | Update Addresses | Customer can update their saved addresses | Yes | My Account_View Details
|  |  | 28 | Address Book | Customer can view address book | Yes | My Account_View Details
|  | VIP Program | 29 | Upgrade | Qualified customers can upgrade from normal account to VIP account to enjoy VIP programs | No | My Account_VIP Program
|  | My Orders | 30 | Order List | Customer can view the list of orders they placed on the website | Yes | My Account_My Orders
|  |  | 31 | Order Detail | Customer can view details and status of each order they placed on the website | Yes | My Account_My Orders
|  |  | 32 | Track Delivery | Customer can track the delivery status for each item in an order | Yes | My Account_My Orders
|  |  | 33 | Track Order Status | Customer can track order status and will be informed via emails when there's an update | Yes | My Account_My Orders
|  |  | 34 | View Invoice | Customer can view and print invoice of their order | Yes | My Account_My Orders
|  |  | 35 | Cancel Order | Customer can cancel an order if it has not been processed for fulfillment | No | My Account_My Orders
|  |  | 36 | Request Return | Customer can request to return a received product as long as it satisfies the Return T&Cs of each country | Yes | My Account_My Orders
|  | My Returns | 37 | View Return Orders | Customer can view and track status of their return orders | Yes | My Account_My Returns
|  | My Refund | 38 | View Refunds | Customer can view their refunds of cancelled and returned orders | Yes | My Account_My Refund
|  | Others | 39 | Newsletter Subscription | Logged-in customer can subscribe or unsubscribe to newsletters. Customer receives email confirmation of subscription and unsubscription. | Yes | My Account_Others
|  | Inquiries | 40 | Go to call appointment |  | Yes | My Account_Inquiries
|  |  | 41 | Go to email |  | Yes | My Account_Inquiries
| Others |  | 42 | Need Help | Customer can view Need Help Block on Shopping cart page, shipping address page, billing address page, order complete page, track my order page, guest order detail page, guest invoice details page, guest return detail page, and guest refund detail page. | Yes | Others_FEPages
|  |  | 43 | Track My Order | Customer (including guest) can track their order's statuses. | Yes | Others_FEPages
|  |  | 44 | FAQ | Customer can view FAQ page (same as on lg.com) | Yes | Others_FEPages
Admin Site | DASHBOARD | Dashboard | 45 | Dashboard | Same as Magento default. | Yes | Admin_Dashboard
| SALES | Orders | 46 | View Order | Admin can view Sales Orders of countries they are assigned to | Yes | Admin_SALES_Orders
|  |  | 47 | Update Order | Authorized Admin can update Sales Orders of countries they are assigned to | Yes | Admin_SALES_Orders
|  |  | 48 | Cancel Order | Admin can cancel an order on customer's behalf if it has not been processed for fulfillment | Yes | Admin_SALES_Orders
|  |  | 49 | Request Return | Admin can create return request on behalf of a customer | Yes | Admin_SALES_Orders
|  | Invoices | 50 | Create Invoice | Magento Invoice is automatically created after successful payment | Yes | Admin_SALES_Invoices
|  |  | 51 | Print Invoice | Admin can print invoice once it's available | Yes | Admin_SALES_Invoices
|  | Shipments | 52 | Create Shipment | Shipment is automatically created upon conditions are met. | Yes | Admin_SALES_Shipments
|  |  | 53 | Update Shipping Statuses | Shipping Statuses are automatically updated in sync with actual shipping progress | Yes | Admin_SALES_Shipments
|  | Returns | 54 | Returns | OBS operators can authorize/deny, approve/reject, comment on return request | Yes | Admin_SALES_Returns
|  |  | 55 | Update Return Statuses | Return Statuses are automatically updated in sync with actual return progress | Yes | Admin_SALES_Returns
|  | Credit Memos | 56 | Cancel Credit Memo | Credit memo can be automatically created upon order is canceled. | Yes | Admin_SALES_Credit Memos
|  |  | 57 | Return Credit Memo | Credit memo can be automatically created upon return order is completed. | No | Admin_SALES_Credit Memos
|  |  | 58 | Online Refund | OBS operator can refund online for a qualified return. Refund request is sent to Payment Gateway and handled automatically | Yes | Admin_SALES_Credit Memos
| CATALOG | Product Management | 59 | Create Simple Products from GERP | Simple product is automatically created from GERP'S MDM, Price Info, Stock Updates. | Yes | Admin_Product
|  |  | 60 | Create Simple Products from S2K | Simple product is automatically created from getting S2K product list. | No | Admin_Product
|  |  | 61 | Update Carriers & Delivery Type | Product Carriers and Delivery Type is automatically updated from Store Configuration Setting when product is created | Yes | Admin_Product
|  |  | 62 | Create Configurable Products | Configurable product is automatically created from LG.COM's CXML file via FTP | Yes | Configurable_Product
|  | Postcode Management | 63 | Postcode Management | OBS Operator can view and search postcode list. | No | Admin_PostCode
| CUSTOMERS | Customer Management | 64 | Create Customer | Customer is automatically created once create an account from lg.com | Yes | Admin_Customer
|  |  | 65 | Delete Customer | Admin can delete a customer from OBS on request | Yes | Admin_Customer
| MARKETING | Content Management | 66 | T&C of Sales | OBS Operator can set up T&C of Sales for their country | Yes | Admin_MARKETING
|  |  | 67 | Privacy policy | OBS Operator can set up for Privacy Policy for their country | Yes | Admin_MARKETING
|  |  | 68 | Cookie policy | OBS Operator can set up for Cookie Policy for their country | Yes | Admin_MARKETING
|  |  | 69 | VIP T&C | OBS Operator can set up VIP Terms and Conditions for their country | Yes | Admin_MARKETING
|  |  | 70 | VIP Privacy Policy | OBS Operator can set up VIP Privacy Policy for their country | Yes | Admin_MARKETING
|  |  | 71 | Return T&C | OBS Operator can set up Return T&C for their country | Yes | Admin_MARKETING
|  |  | 72 | E-mail Templates | OBS Operator can setup templates for the emails that are sent at the statuses of: New Order, Order Cancel, Shipment, Return request, Credit memo[Refund], Newsletter subscription | Yes | Admin_MARKETING
| STORES | General | 73 | Bill-to/Ship-to Code Management | OBS Operator can maintain the list of bill-to/ship-to codes | Yes | STORES_Bill-to/Ship-to Code Management
|  |  | 74 | Configuration/General | Admin can configure the store general information | Yes | STORES_General
|  |  | 75 | Configuration/Customers | Admin can set the customer configuration | Yes | STORES_General
|  |  | 76 | Configuration/Catalog | Admin can set the catalog configuration | Yes | STORES_General
|  |  | 77 | Configuration/Sales | Admin can set the sales configuration. | Yes | STORES_General
|  |  | 78 | Installation | Admin can enable/disable Installation service by Order or by Item level in shipping address page | Yes | STORES_General
|  |  | 79 | Haulaway | Admin can enable/disable Haulaway service by Order or by Item level in shipping address page | No | STORES_General
|  |  | 80 | Configuration/Sales | Admin can set RMA configuration including conditions to allow return | Yes | STORES_General
|  |  | 81 | Configuration/LG/Theme/LG Session _Cookie Setting | Admin can set the cookie link configuration | Yes | STORES_General
|  | Integrations | 82 | Configuration/LG/ECS | Admin can set the ECS API link configuration | Yes
|  |  | 83 | Configuration/LG/SSO/General | Admin can set the SSO configuration | Yes
|  |  | 84 | Configuration/LG/GERP | Admin can set the GERP configuration. Admin can set "Invoice Print Flag" | Yes
|  |  | 85 | Configuration/LG/FTP | Admin can set the FTP file configuration | Yes
| Amasty Extensions |  | 86 | Out of Stock Notifciations | Admin can receive low stock notification based on configurations. Customer can receive restock notification based on configurations. | Yes
Interface | LG.COM Interface |  | 87 | Model Status All Product Service | OBS returns qualified products to lg.com | Yes | LG.COM Interface
|  |  | 88 | Pincode Validation Service | OBS returns stock availbitity and shipping coverage of a product to lg.com based on Pincode | No | GERP Interface
|  |  | 89 | Get Last Orders Service | OBS returns customer's 5 most recent orders to lg.com | Yes
|  |  | 90 | Get Address Book Service | OBS returns customer's 5 most recent addresses to lg.com | Yes
|  |  | 91 | Get Access Token Service | OBS returns customer information to lg.com based on access token. | Yes
|  |  | 92 | Add to cart Service | Customer can add a product from lg.com to cart on OBS | Yes
|  |  | 93 | Create Empty Cart Service | OBS returns an empty cart to lg.com when there is no LG5_CartID in cookie. | Yes
|  |  | 94 | Delete User Service | Customer account can be deleted on lg.com if no associated processing orders. | No
|  |  | 95 | Merge Cart Service | Guest cart and logged-in user's cart are merged | Yes
|  |  | 96 | Login Service | OBS gets customer info from SSO and returns cart id. | Yes
|  |  | 97 | Logout Service | OBS logs out customer once customer is logged out from LG.com | Yes
|  |  | 98 | Keep Alive Service | Customer is logged out after 60 minutes of inactivity. | Yes
|  |  | 99 | Get Cart Info Service | OBS returns cart info to lg.com. | Yes
|  |  | 100 | Product Marketing Information (Configurable Product) | Product data file is sent from lg.com to OBS via FTP | Yes | Configurable_Product
|  |  | 101 | Header/Footer Service | OBS displays the same header/footer as lg.com. | Yes
|  |  | 102 | Postcode Validation API | OBS returns delivery coverage, in-stock status based on entered postcode. | No
|  |  | 103 | VIP Group Price | OBS returns group prices for all qualified products. | No
|  |  | 104 | Customer Group | OBS returns customer group and VIP upgrade URL (if qualified) based on a customer's email address. | No
GERP Interface | GERP>OBS |  | 105 | OMD Product Model master | This is backend function to get and parse Product model master from GERP. | Yes | OMD_Product
|  |  | 106 | OMD Update Model master | This is backend function to get and parse (update) Product model master info from GERP. | Yes | OMD_Product
|  |  | 107 | OMD Product Stock (Reserved Stock) | This is backend function to get and parse Product Stock from GERP. | Yes | OMD_Product
|  |  | 108 | OMD Product Stock (Reserved Stock) | This is backend function to reset stock base on threshold checking condition and update stock | Yes | OMD_Product
|  |  | 109 | OMD Product Price Info | This is backend function to get and parse Price Information from GERP with different rules | Yes | OMD_Product
|  |  | 110 | OMD Product Price Info | Update price and check expiration date to disable automatically product in special conditions | Yes | OMD_Product
|  |  | 111 | OMV Product | OMV products are created and price and stock are updated with ACC_MDM, ACC_STOCK. | Yes | OMV_Product
|  |  | 112 | Order Export - order | This is backend function to send order information to GERP. | Yes | GERP Interface
|  |  | 113 | Order Export - cancel | This is backend function to send cancel information to GERP with different case - Cancel after order export but before receive status from GERP -Cancel after order export and after receive status from GERP | Yes | GERP Interface
|  |  | 114 | Order Export - return | This is backend function to send return information to GERP after return request authorization. | Yes | GERP Interface
|  |  | 115 | Product Order Back I/F | This is backend function to get order processing result from GERP. | Yes | GERP Interface
|  |  | 116 | Product Order status | This is backend function to get order status result from GERP and update status for Item and order | Yes | GERP Interface
|  |  | 117 | Shipping Method Code [SE only] | This is backend function to map Carrier Code with Delivery Type | Yes | GERP Interface
|  |  | 118 | Cancelled status from GERP | This is backend function to get CANCELLED status from GERP and update status for Item and order and create crediut memo and refund | Yes | GERP Interface
|  |  | 119 | API Connector | Make the connection work between OBS - ECS - GERP and GERP - ECS - OBS | Yes | GERP Interface
Chile OBS unique features |  |  | 120 |  | Admin is able to view PTO products synced from GERP | Yes | PTO_ Product
|  |  | 121 |  | Admin is able to view stock of PTO products synced from GERP | Yes | PTO_ Product
|  |  | 122 |  | Admin is able to view price of PTO products synced from GERP | Yes | PTO_ Product
|  |  | 123 |  | Customers are able to view PTO products on LG.com | Yes | PTO_ Product
|  |  | 124 |  | Admin is able to manage 2 shipping warehouses | Yes
|  |  | 125 |  | Admin is able to view stock synced from GERP to OBS | Yes
|  |  | 126 |  | Customers are able to add new Shipping address. Customers are able to select a Region in the list. Customers are able to select a Comuna in the list. Comuna list is shown based on the selected Region. | Yes
|  |  | 127 |  | Admin is able to manage Comuna by Region | Yes
|  |  | 128 |  | Customers are able to see Installation fee | Yes
|  |  | 129 |  | Admin is able to manage Installation fee | Yes
|  |  | 130 |  | Customers are able to view Delivery days | Yes
|  |  | 131 |  | Admin is able to manage Delivery days by Products and Comuna | Yes
|  |  | 132 |  | Customers are able to view Delivery Cost | Yes
|  |  | 133 |  | Admin is able to manage Delivery Cost by Products and Comuna | Yes
|  |  | 134 |  | Single Tax: 19% for all products GERP price: without VAT OBS price: include VAT Customers are able to see price including VAT | Yes
|  |  | 135 |  | Customers are able to see VAT amount on Order Summary: 1. Shopping Cart 2. Checkout 3. Order detail | Yes
|  |  | 136 |  | Additional tax | No
|  |  | 137 |  | Admin is able to create Bundles | Yes

## OMD_Product (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | OMD Product | [5 empty] | Pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written By | KhuyenTL | Reviewed By | DuongTTT |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-05-28 | Reviewed Date |  |  |  |  | Untested | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 35
Execute by |  | Execute Date |  |  |  |  | N/A | 4 | 39 | 39 | 39 | 39 | 39 | 39 | 160
Test data | [6 empty] | Total of TC | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 195
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
| GERP master information |  | https://docs.google.com/spreadsheets/d/1nKXXVAB41JnEfJ3aQUDvtVi2_uwPUDnt/edit#gid=1261367591 | Value of Chile: + "AFFILIATE_CODE" : "EECL", + "LEGAL_ENTITY_NAME" : "LGECL", | Low | Sprint 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| GERP cron job |  | https://docs.google.com/document/d/1a6FDV8pQoj3fR-oqWuiY1GewAIYqp8IG/edit | Create OMD Product: - job name: gerp_omd_import_product_creates - cron execute function: \Lg\Gerp\Cron\OmdProductCreate::execute - cron schedule: 0 */4 * * * | Low | Sprint 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Link download .json for Postman | Bản đầy đủ nhưng bị lỗi endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1zROPtLKGJ17dOWmhsWE-iaCGbpaLqvtA |  | Low | Sprint 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | Bản backup để lấy content endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1ttlmHWfCQiUuSwOe_CEWq18KDjomljxI |  | Low | Sprint 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Configuration in BE
Pre-condition: - Connect server and Database successfully base on guide https://docs.google.com/document/d/1PXqn6DKNKSxBCGveSnKc6T3XLwda7PteoZ-2fde9Kv8/edit
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Create simple product
Pre-condition: - Connect server and Database successfully base on guide https://docs.google.com/document/d/1PXqn6DKNKSxBCGveSnKc6T3XLwda7PteoZ-2fde9Kv8/edit
[FN-2] | Create Master product |  | 1. Import all ECSS json to Postman 2. Open ECSS_Product Model Master request. 3. Edit server URL: https://stg.obs.lg.com 4. Edit Body with: "INTERFACE_ID" : "9000001", "MODEL_CODE" : "KH.OMD9000001", "SALES_MODEL_CODE" : "KH.OMD9000001", "AFFILIATE_CODE" : "EECL", "LEGAL_ENTITY_NAME" : "LGECL", 5. Send request | 5. Request is sent successfully Product is create in MQDB / Table xxinvs_model_s_if which satisfy: SELECT * FROM mqdb_stg.xxinvs_model_s_if where SALES_MODEL_CODE = MODEL_CODE value; | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Create simple product
Pre-condition: - Connect server and Database successfully base on guide https://docs.google.com/document/d/1PXqn6DKNKSxBCGveSnKc6T3XLwda7PteoZ-2fde9Kv8/edit
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A

## OMV_Product (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | PTO Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 39 | 39 | 39 | 39 | 39 | 39 | 156
Test data | [6 empty] | Total of TC | 40 | 39 | 39 | 39 | 39 | 39 | 39 | 196
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | GERP master information |  | https://docs.google.com/spreadsheets/d/1nKXXVAB41JnEfJ3aQUDvtVi2_uwPUDnt/edit#gid=1261367591 | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-1] | GERP cron job |  | https://docs.google.com/document/d/1a6FDV8pQoj3fR-oqWuiY1GewAIYqp8IG/edit | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-2] | Link download .json for Postman | Bản đầy đủ nhưng bị lỗi endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1zROPtLKGJ17dOWmhsWE-iaCGbpaLqvtA | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-3] |  | Bản backup để lấy content endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1ttlmHWfCQiUuSwOe_CEWq18KDjomljxI | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A

## PTO_Product (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | PTO Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 39 | 39 | 39 | 39 | 39 | 39 | 156
Test data | [6 empty] | Total of TC | 40 | 39 | 39 | 39 | 39 | 39 | 39 | 196
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | GERP master information |  | https://docs.google.com/spreadsheets/d/1nKXXVAB41JnEfJ3aQUDvtVi2_uwPUDnt/edit#gid=1261367591 | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-1] | GERP cron job |  | https://docs.google.com/document/d/1a6FDV8pQoj3fR-oqWuiY1GewAIYqp8IG/edit | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-2] | Link download .json for Postman | Bản đầy đủ nhưng bị lỗi endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1zROPtLKGJ17dOWmhsWE-iaCGbpaLqvtA | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-3] |  | Bản backup để lấy content endpoint ECSS_Parts Stock | https://drive.google.com/drive/u/0/folders/1ttlmHWfCQiUuSwOe_CEWq18KDjomljxI | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A

## Admin
ID | Screen | Function | Steps to execute | Test Data | Expected output | Test result | Note
1 | Quản lý danh mục | Thêm mới | 1. Click button "Thêm danh mục" 2. Nhập tên danh mục 3. Click button "Thêm danh mục" | Thêm danh mục "Son môi - Lips" | 1. Thêm danh mục thành công 2. Danh mục mới thêm hiển thị lên danh sách danh mục sản phẩm ở cả giao diện Admin và giao diện Khách hàng | Pass
2 |  | Sửa | 1. Click button "Sửa" 2. Sửa tên danh mục 3. Click button "Sửa danh mục" | Sửa danh mục "Trang điểm - Makeup" thành danh mục "Đồ trang điểm" | 1. Sửa danh mục thành công 2. Danh mục mới sửa hiển thị lên danh sách danh mục sản phẩm ở cả giao diện Admin và giao diện Khách hàng | Pass
3 |  | Xóa danh mục khi có sản phẩm | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" | Chọn danh mục cần xóa "Đồ trang điểm" | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa danh mục này không ?" 2. Hiển thị màn hình thông báo "Chỉ được xóa danh mục không có sản phẩm" | Pass
4 |  | Xóa danh mục khi không có sản phẩm | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" | Chọn danh mục cần xóa "Son môi - Lips" | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa danh mục này không ?" 2. Danh mục được xóa khỏi danh sách danh mục ở giao diện Admin và giao diện khách hàng | Pass
5 | Quản lý hãng sản xuất | Thêm mới | 1. Click button "Thêm hãng sản xuất" 2. Nhập tên hãng sản xuất 3. Click button "Thêm hãng sản xuất" | Thêm danh mục "DHC" | 1. Thêm hãng sản xuất thành công 2. Hãng sản xuất mới thêm hiển thị lên danh sách hãng sản xuất | Pass
6 |  | Sửa | 1. Click button "Sửa" 2. Sửa tên hãng sản xuất 3. Click button "Sửa hãng sản xuất" | Sửa hãng sản xuất "SENKA" thành hãng sản xuất "SENKA 123" | 1. Sửa hãng sản xuất thành công 2. Hãng sản xuất mới sửa hiển thị lên danh sách hãng sản xuất | Pass
7 |  | Xóa hãng sản xuất khi có sản phẩm | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" | Chọn hãng sản xuất cần xóa "Neutrogena" | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa hãng sản xuất này không ?" 2. Hiển thị màn hình thông báo "Chỉ được xóa hãng sản xuất không có sản phẩm" | Pass
8 |  | Xóa hãng sản xuất khi không có sản phẩm | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" | Chọn danh mục cần xóa "SENKA" | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa hãng sản xuất này không ?" 2. Hãng sản xuất được xóa khỏi danh sách hãng sản xuất | Pass
9 | Quản lý sản phẩm | Thêm mới | 1. Click button "Thêm sản phẩm" 2. Nhập tên sản phẩm, danh mục, hãng sản xuất, giá, giá khuyến mãi (nếu có)ảnh sản phẩm và chi tiết 3. Click button "Thêm sản phẩm" |  | 1. Thêm sản phẩm thành công 2. Sản phẩm mới thêm hiển thị lên danh sách sản phẩm ở cả Admin và khách hàng | Pass
10 |  | Sửa | 1. Click button "Sửa" 2.Sửa thông tin sản phẩm 3. Click button "Sửa sản phẩm" |  | 1. Sửa sản phẩm thành công 2. Sản phẩm mới sửa hiển thị lên danh sách sản phẩm ở cả Admin và Khách hàng | Pass
11 |  | Dừng bán | 1. Click button "Xóa" 2. Hiển thị popup xác nhận dừng bán 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn dừng bán sản phẩm này không? 2. Sản phẩm được dừng bán không hiển thị lên trang của khách hàng | Pass
12 |  | Bán | 1. Click button "Bán" 2. Hiển thị popup xác nhận bán 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn tiếp tục bán sản phẩm này không?" 2. Sản phẩm được tiếp tục bán và hiển thị lên trang của khách hàng | Pass
13 | Quản lý người dung | Thêm mới | 1. Click button "Thêm tài khoản" 2. Nhập họ và tên, chọn phân quyền, email mật khẩu và hình ảnh đại diện 3. Click button "Thêm sản phẩm" |  | 1. Thêm tài khoản thành công 2. Người dùng có thể đăng nhập được bằng tài khoản đó theo phân quyền | Pass
14 |  | Sửa | 1. Click button "Sửa" 2.Sửa thông tin người dùng 3. Click button "Cập nhật" |  | 1. Sửa tài khoản thành công 2. Hiển thị người dùng theo thông tin mới cập nhật | Pass
15 |  | Xóa người dùng khi không có đơn hàng nào đã đặt | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa người dùng này không ?" 2. Người dùng không hiển thị lên danh sách người dùng. | Pass
16 |  | Xóa người dùng khi có đơn hàng nào đã đặt | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa người dùng này không ?" 2.Hiển thị nàn hình thông báo "Chỉ được xóa tài khoản chưa đặt đơn hàng nào" | Pass
17 | Bình luận | Xem chi tiết các bình luận | 1. Click "Chi tiết" |  | 1. Màn hình trở về giao diện website 2. Admin xem các bình luận đánh giá | Pass
18 |  | Trả lời bình luận | 1. Click "Trả lời" 2. Nhập nội dung bình luận 3. Click button "Trả lờit" |  | 1. Trả lời bình luận thành công 2. Hiển thị bình luận theo từng người dùng | Pass
19 | Bình luận | Xem chi tiết các bình luận | 1. Click "Chi tiết" |  | 1. Màn hình trở về giao diện website 2. Admin xem các bình luận đánh giá | Pass
20 |  | Trả lời bình luận | 1. Click "Trả lời" 2. Nhập nội dung bình luận 3. Click button "Trả lờit" |  | 1. Trả lời bình luận thành công 2. Hiển thị bình luận theo từng người dùng | Pass
21 | Giỏ hàng | Cập nhật trạng thái đơn hàng | 1. Click button "Cập nhật" 2. Hiển thị popup xác nhận 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn xác nhận đơn hàng này đã giao thành công ?" 2. Trạng thái đơn hàng đươc chuyển đổi | Pass
22 | Slide | Thêm Slide | 1. Click button "Thêm Slide" 2. Nhập thông tin slide 3. Click button "Thêm Slide" |  | 1. Slide mới thêm được hiển thị trong danh sách slide ở Admin 2. Hình ảnh Slide mới được hiển thị trong mục Slide quảng cáo bên giao diện khách hàng | Pass
23 |  | Sửa Slide | 1. Click button "Sửa Slide" 2. Nhập thông tin slide 3. Click button "Cập nhật" |  | 1. Slide mới sửa được hiển thị trong danh sách slide ở Admin 2. Hình ảnh Slide mới được hiển thị trong mục Slide quảng cáo bên giao diện khách hàng | Pass
24 |  | Xóa Slide | 1. Click button "Xóa" 2. Hiển thị popup xác nhận xóa 3. Click button "OK" |  | 1. Hiển thị màn hình thông báo "Bạn có muốn xóa Slide này không ?" 2. Slide mới sửa được hiển thị trong danh sách slide ở Admin 3. Hình ảnh Slide mới được hiển thị trong mục Slide quảng cáo bên giao diện khách hàng | Pass
25 | Thông tin website | Sửa thông tin website | 1. Click button "Sửa" 2. Nhập thông tin website 3. Click button "Cập nhật" |  | 1. Các thông tin website được cập nhật thành cồn và hiển thị lên màn hình Admin. 2. Các thông tin website được hiển thị đúng trên giao diện khách hàng. | Pass

## Khách hàng
ID | Screen | Function | Steps to execute | Test Data | Expected output | Test result | Note
1 | Tìm kiếm | Tìm kiếm theo tên danh mục | 1. Click vào tên danh mục | Click vào danh mục "Đố trang điểm" | 1. Hiển thị danh sách sản phaame liên quan đến danh mục sản phẩm click | Pass
2 |  | Tìm kiếm theo tên sản phẩm | 1. Click vào ô tìm kiếm 2. Nhập tên sản phẩm cần tìm 3. Nhấn nút Enter | Nhập từ "hoa" | 1. Hiển thị danh sách các sản phẩm liên quan đến từ tìm kiếm | Pass
3 | Chi tiết sản phẩm | Xem trang chi tiết sản phẩm | 1. Chọn sản phẩm cần xem 2. Click vào tên sản phẩm | Chọn sản phẩm | 1. Hiển thị phần chi tiết của sản phẩm | Pass
4 | Check giá của sản phẩm | Giá sản phẩm khi chưa có giá khuyến mãi | 1. Chọn sản phẩm cần kiểm tra 2. Quan sát giá của sản phẩm |  | 1. Giá của sản phẩm hiển thị đúng theo dữ liệu trong admin và databasse | Pass
5 |  | Giá sản phẩm khi đã có giá khuyến mãi | 1. Chọn sản phẩm cần kiểm tra 2. Quan sát giá của sản phẩm |  | 1. Gía của sản phẩm hiển thị lên giao diện khách hàng sẽ được tính theo công thức: giá sản phẩm * ((100 - giá khuyến mãi)/100) | Pass
6 | Thêm vào giỏ hàng | Giỏ hàng trống | 1. Click icon giỏ hàng |  | 1. Giỏ hàng không có sản phẩm nào
7 |  | Giỏ hàng có sản phẩm | 1. Thêm sản phẩm vào giỏ hàng 2. Click icon giỏ hàng |  | 1. Icon giỏ hàng hiển thị số lượng sản phẩm theo từng loại sản phẩm trong giỏ hàng 2. gGỏ hàng hiển thị sản phẩm kèm theo giá của từng loại sản phẩm | Pass
8 |  | Xem sản phẩm trong giỏ hàng | 1. Click vào tên sản phẩm/ icon giỏ hàng 2. Chọn số lượng sản phẩm 3. Click button "Thêm giỏ hàng" |  | 1. Sản phẩm được thêm vào giỏ hàng theo số lượng đã chọn | Pass
9 |  | Giá hiển thị trong giỏ hàng | 1. Thêm sản phẩm vào giỏ hàng 2. Kiểm tra giá của từng sản phẩm và tổng tiền |  | 1. Gía của tùng sản phẩm được tính theo công thức: số lượng *giá sản phẩm. 2. Tổng tiền được cộng từ tổng các sản phẩm trong giỏ hàng | Pass
10 | Đơn hàng | Xem đơn hàng | 1. Thêm sản phẩm vào giỏ hàng 2. Click button "Đặt hàng" |  | 1. Hiển thị màn hình giao diện giỏ hàng | Pass
11 |  | Xóa sản phẩm | 1. Thêm sản pẩm vào giỏ hàng 2. Click button "Đặt hàng" 3. Click icon delete |  | 1. Không hiển thị sản phẩm bị xóa sau khi click icon delete | Pass
13 |  | Đặt hàng thành công | 1. Thêm sản pẩm vào giỏ hàng 2. Click button "Đặt hàng" 3. Nhập địa chỉ giao hàng 4. Click button "Đặt hàng" |  | 1. Giỏ hàng quay về trống | Pass
15 |  | Kiểm tra giá của đơn hàng | 1. Thêm sản pẩm vào giỏ hàng 2. Click button "Đặt hàng" 3. Quan sát giá của đơn hàng |  | 1. Giá của cả đơn hàng sẽ bằng tổng các sản phẩm và cộng thêm 30.000 tiền ship đồng giá. | Pass
16 | Lịch sử đặt hàng | Sau khi đặt hàng thành công | 1. Đặt hàng thành công 2. Click button "Lịch sử đặt hàng" |  | 1. Sau khi khách hàng đặt hàng thành công. Trạng thái đơn hàng là "Đang giao---" | Pass
17 |  | Kiểm tra giá của đơn hàng | 1. Đặt hàng thành công 2. Click button "Lịch sử đặt hàng" |  | 1. Sau khi đặt hàng thành công giá của đơn hàng mới chưa được cộng vào tổng giá trị tài khoản đã mua. | Pass
18 |  | Sau khi admin cập nhật đơn hàng | 1. Đặt hàng thành công 2. Click button "Lịch sử đặt hàng" 3. Admin cập nhật đơn hàng |  | 1. Trạng thái của đơn hàng sẽ được chuyển đổi sang "Thành công" | Pass
19 |  | Kiểm tra giá của đơn hàng | 1. Đặt hàng thành công 2. Click button "Lịch sử đặt hàng" 3. Admin cập nhật đơn hàng |  | 1. Tổng giá trị tài khoản đã mua sẽ cộng thêm giá mà khách hàng vừa đặt đơn mới trừ đi phí ship | Pass

## Configurable_Product (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 39
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 39 | 39 | 39 | 39 | 39 | 39 | 156
Test data | [6 empty] | Total of TC | 40 | 39 | 39 | 39 | 39 | 39 | 39 | 196
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1 | Untested | N/A | N/A | N/A | N/A | N/A | N/A

## Guest_Checkout (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 32
Test data | [6 empty] | Total of TC | 9 | 8 | 8 | 8 | 8 | 8 | 8 | 41
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Untested | N/A | N/A | N/A | N/A | N/A | N/A
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1

## Customer_Authorize (hidden)
` | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test data | [6 empty] | Total of TC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1

## Customer_Checkout (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test data | [6 empty] | Total of TC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1

## Customer_Order (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test data | [6 empty] | Total of TC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1

## Customer_Cancel_Return (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | Configurable_Product | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test data | [6 empty] | Total of TC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1

## System_Test (hidden)
Project Name | LGOBS | [6 empty] | PC- Chrome | Firefox (lastest) | Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ | Ipad mini 4 | Samsung Galaxy 7 | SUM
Feature Name | System Test | [5 empty] | Pass | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Written By | HuyenBT2 | Reviewed By | TrangPT4 |  |  |  | Fail | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Written Date | 2021-04-28 | Reviewed Date |  |  |  |  | Untested | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execute by | HuyenBT2 | Execute Date |  |  |  |  | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Test data | [6 empty] | Total of TC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ID | Flow | Scenario | Steps to execute | Expected output | Priority | Sprint | Test result | [6 empty] | Jira Bug | Note
[7 empty] | Windows 10-Chrome (lastest) | Windows 10-Firefox (lastest) | Windows 10-Edge (lastest) | MacOS-Safari (lastest) | iPhone 7+ -Safari (lastest) | Ipad mini 4 -Safari (lastest) | SS Galaxy 7 -Safari (lastest)
"OMD_Product" function
Refer links
Pre-condition: - -
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-1] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-2] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-3] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-4] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[5 empty] | Low | Sprint 0
[5 empty] | Low | Sprint 0
Configration in BE
Pre-condition: - -
[FN-5] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-6] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-7] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Function
Pre-condition: - -
[FN-8] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-9] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-10] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-11] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-12] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-13] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-14] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-15] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-16] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-17] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-18] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-19] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-20] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-21] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-22] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-23] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-24] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-25] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-26] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-27] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-28] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-29] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-30] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-31] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-32] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-33] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
[FN-34] | Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0
Fill in the flow | Fill in the scenario (sub-flow) | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-36] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-37] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1
[FN-38] |  | fill in the step | Fill in the expected here | Low | Sprint 0 | Sprint 1